## In Progress
ID | Title | Status | Estimated Hours | Burning Hours | Work Completed Today | Work to be completed tomorrow | Blockers/Impediments (if any)
96646 | BA Audatex Activities | Investigation In Progress | 5 | 4
138029 | DEV INV MIAFTR integration change - Regulatory change (MIAFTR to deliver by May '22 - NFUM to deliver Q4 - Timeline to be agreed) | Development In Progress
96467 | Auto-send DOC003 on all new Motor Claims | Completed
96642 | Support Migrated Claims (linked to US11047) Search functionality within the documents screen on ClaimCenter (DEV INV completed in 2103) | Completed
145257 | DEV & TEST: Technical INC000022064255 -Audatex Batch failed with reason is not formatted correctly for the field "PolicyNumber": Exceeds the maximum length 20 | Completed
143611 | Driver Specific Excess not being applied (DEV INV completed in 2103) | Completed
| Audatex LLD Document - Self Study | In Progress |  | 3 | No | Yes
120
Note on D9: Abhimanyu Kumar: